## Sprint Dashboard
ZYLO AI READINESS SPRINT — FACILITATOR DASHBOARD
Internal Use Only ¦ Sprint Lead + Business Analyst
CLIENT INFORMATION
Client Company Name
Primary Contact (CEO/Founder)
Contact Email
Contact Phone / WhatsApp
Company Industry
Company Headcount
Estimated Annual Revenue
Headquarters Location
Sprint Confirmed Date
SPRINT TEAM ASSIGNMENT
Role | Name | Email | Phone/WhatsApp | Notes
Sprint Lead — AI Strategy Consultant
Business Analyst
Technical Architect (Day 3+)
Sales Rep / Account Manager
SPRINT SCHEDULE
Day | Date | Time (Start) | Duration | Format | Key Attendees Required | Zoom Link | Status
Day 1 |  |  | 4–6 hours | Zoom / In-person | CEO (required) + COO + 1 Dept Head |  | Scheduled
Day 2 |  |  | 4–5 hours | Zoom / In-person | Ops Lead / IT Manager |  | Scheduled
Day 3 AM |  |  | 3–4 hours | Internal Only | Sprint Lead + Technical Architect |  | Internal
Day 3 PM |  |  | 2 hours | Zoom / In-person | CEO + Key Stakeholders |  | Scheduled
Day 4 |  |  | 3–4 hours | Zoom / In-person | CEO + Ops Lead |  | Scheduled
Day 5 |  |  | 2.5–3 hours | Zoom / In-person | CEO + ALL Stakeholders + Investors if possible |  | CRITICAL
PRE-SPRINT CHECKLIST
# | Checklist Item | Owner | Due By | Done?
1 | Qualification call completed — confirmed budget authority + AI intent | Rep | Before sprint confirmed | ☐
2 | NDA signed via DocuSign | Rep | Before Day 1 | ☐
3 | Client Workbook (Pre-Sale) sent to client | Rep | 3 days before Day 1 | ☐
4 | Client Workbook Business Profile section received back | Rep | 24h before Day 1 | ☐
5 | Sprint Lead briefed on playbook and client context | Sprint Lead | 48h before Day 1 | ☐
6 | Pre-Sprint Research Brief completed by Sprint Lead | Sprint Lead | 48h before Day 1 | ☐
7 | Technical Architect briefed and Day 3 availability confirmed | Sprint Lead | 48h before Day 1 | ☐
8 | Day 1 agenda sent to client | Rep | 48h before Day 1 | ☐
9 | Zoom links created and tested for all 5 days | Rep | 24h before Day 1 | ☐
10 | All sprint team contacts shared with client | Rep | Before Day 1 | ☐

## Day 1 — Discovery
DAY 1 — BUSINESS DISCOVERY & STAKEHOLDER ALIGNMENT
Sprint Lead runs all sessions ¦ BA captures everything ¦ DO NOT PITCH on Day 1
SESSION 1 (AM): COMPANY OVERVIEW & GOALS
⚑ Key rule: Ask more questions than you answer. Your job today is to listen, understand, and build trust.
# | Discovery Question (AM Session) | Client Answer / Notes | Follow-Up Required?
1 | What does the company do and who are your primary customers?
2 | What are your main revenue streams and approximate revenue breakdown?
3 | How many full-time employees and what are the main departments?
4 | What does "winning" look like for this business in 12 months?
5 | What are the 3 biggest strategic priorities for the next 12 months?
6 | What is currently holding you back from those priorities?
7 | Who are your main competitors and how do you differentiate?
8 | What technology investments have you made in the last 2 years?
SESSION 2 (PM): PAIN POINTS & PROCESS DEEP-DIVE
# | Discovery Question (PM Session) | Client Answer / Notes | Process Flagged? | Priority (H/M/L)
1 | Walk us through a typical week for your operations team — what does it look like?
2 | Where does your team spend the most time on work that doesn't require human judgment?
3 | Where do errors, delays, or miscommunications happen most often?
4 | What would you automate first if cost and complexity were no object?
5 | What reports or data do you wish you had but currently don't?
6 | Where are customers having a poor experience due to slow internal processes?
7 | What manual handoffs exist between departments that cause delays?
8 | What data do you already have that you're not currently using?
9 | How long does it take to onboard a new client end-to-end?
10 | If your best operations person left tomorrow, what knowledge would be lost?
PROCESS INVENTORY LOG — Capture All Manual Processes Identified Today
# | Process Name | Department | Description (what happens manually) | Est. Hours/Week | Owner | Frequency | Initial Priority
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
DAY 1 SUMMARY — Complete Before End of Day
Top 3 Pain Areas Identified (in priority order)
Business Goals Summary (what "winning" looks like in 12 months)
Key Stakeholder Dynamics (who has the real influence in this company?)
Hypothesis confirmed from Pre-Sprint Brief
New hypothesis raised by Day 1 (not in Pre-Sprint Brief)
Red flags or risks noticed (budget concerns, scepticism, complexity)
Day 1 client energy level (Engaged / Neutral / Cautious)
Action items before Day 2

## Day 2 — Assessment
DAY 2 — CURRENT STATE ASSESSMENT
Zylo AI Readiness Matrix™ ¦ Score each process across 4 dimensions ¦ Scale: 1 (lowest) to 5 (highest)
SCORING GUIDE: Axis 1: Process Maturity (1=Chaotic→5=Optimised) ¦ Axis 2: Data Readiness (1=No Data→5=Rich) ¦ Axis 3: Business Impact (1=Negligible→5=Critical) ¦ Axis 4: Integration Complexity (1=Very Complex→5=Simple)
FORMULA: AI Priority Index = (Axis1 × 1.0) + (Axis2 × 1.5) + (Axis3 × 2.0) + (Axis4 × 1.5) ¦ Max = 30 ¦ AI Readiness Score = (API ÷ 30) × 100
# | Process Name | Department | Axis 1 Process Maturity | Axis 2 Data Readiness | Axis 3 Business Impact | Axis 4 Integration Complexity | AI Priority Index (API) | AI Score (/100) | Notes / Data Sources
1 | Lead Gen |  | 2 | 1 | 3 | 1 | 11 | 37
2
3
4
5
6
7
8
9
10
11
12
13
14
15
| COMPANY AI READINESS SCORE | [5 empty] | #VALUE! | #VALUE! | ← This is the client's AI Readiness Score (0–33=Starter ¦ 34–66=Builder ¦ 67–100=Scaler)
TECHNOLOGY STACK AUDIT
Category | System / Tool | Version / Plan | API Available? | Data Quality | Integration Notes
CRM
ERP / Operations
Accounting / Finance
Communication (email/chat)
Marketing Automation
Analytics / Reporting
Project Management
Cloud / Infrastructure
Custom / Other
DATA INVENTORY
Data Type | Where Stored | Volume / History | Quality (1-5) | Accessible? | Notes for AI Use
Customer / CRM data
Transaction / Sales history
Operational / Process logs
Financial records
Communication data (emails, tickets)
Product / Inventory data
HR / Team data

## Day 3 — Opportunity Map
DAY 3 — AI OPPORTUNITY MAP
Morning: Internal Zylo work only ¦ Afternoon: Present to client for validation
AI Types: A = AI Agent ¦ WA = Workflow Automation ¦ PA = Predictive Analytics ¦ DI = Document Intelligence ¦ DA = Data & Dashboard
# | Opportunity Name (Plain Language) | Department | AI Type (A/WA/PA/DI/DA) | Axis 1 Process Maturity | Axis 2 Data Ready | Axis 3 Impact | Axis 4 Complexity | AI Priority Index | Est. Build Time (wks) | Phase (1/2/3) | Description & Expected Outcome
1
2
3
4
5
6
7
8
9
10
11
12
TOP 5 PRIORITIES — Validated by Client in Day 3 Afternoon Session
Rank | Opportunity Name | AI Priority Index | Phase | Client Reaction | Confirmed? (Y/N)
1
2
3
4
5
⚑ Facilitator Note: In the client session, present the full map first, then ask: "Which of these opportunities excites you most? Which concerns you? Are there any we've missed?" Validate, don't sell.

## Day 4 — ROI Model
DAY 4 — PRIORITISATION & ROI MODEL
Build ROI model for Top 5 opportunities ¦ Use client's actual cost data ¦ Never use generic assumptions without flagging them
COLOUR GUIDE: Blue text = hardcoded inputs (client provides) ¦ Black text = calculated by formula ¦ Yellow background = key assumption cell needing attention
CLIENT COST ASSUMPTIONS — Get from CEO/Ops Lead on Day 4
Assumption | Value | Unit | Source / Notes
Average hourly cost per employee (fully-loaded) | 4 | $/hour
Senior employee hourly rate (managers/specialists) | 6 | $/hour
Average monthly revenue per customer | 2 | $
Monthly customer churn rate (current) | 6 | %
Average cost of a customer complaint / error | 4 | $
Number of full-time employees | 2 | headcount
OPPORTUNITY 1 — ROI MODEL
Opportunity Name
AI Type
Brief Description
ROI Input | Value | Unit | Formula / Basis | Annual Value ($)
Hours saved per week (estimated) |  | hrs/wk | From Day 2 process scoring
Hourly cost used | 4 | $/hr | From assumptions above
Annual labour saving | 1222 | $ | #ERROR!
Error / rework reduction (annual) |  | $ | Estimated from Day 1/2 findings
Build cost estimate (one-time) |  | $ | From Technical Architect estimate
Annual maintenance cost |  | $ | Typically 15-20% of build cost
Net Year 1 ROI |  | $ | #ERROR!
ROI Payback Period |  | months | #ERROR!
OPPORTUNITY 2 — ROI MODEL
Opportunity Name
AI Type
Brief Description
ROI Input | Value | Unit | Formula / Basis | Annual Value ($)
Hours saved per week (estimated) |  | hrs/wk | From Day 2 process scoring
Hourly cost used | 4 | $/hr | From assumptions above
Annual labour saving |  | $ | #ERROR!
Error / rework reduction (annual) |  | $ | Estimated from Day 1/2 findings
Build cost estimate (one-time) |  | $ | From Technical Architect estimate
Annual maintenance cost |  | $ | Typically 15-20% of build cost
Net Year 1 ROI |  | $ | #ERROR!
ROI Payback Period |  | months | #ERROR!
OPPORTUNITY 3 — ROI MODEL
Opportunity Name
AI Type
Brief Description
ROI Input | Value | Unit | Formula / Basis | Annual Value ($)
Hours saved per week (estimated) |  | hrs/wk | From Day 2 process scoring
Hourly cost used | 4 | $/hr | From assumptions above
Annual labour saving |  | $ | #ERROR!
Error / rework reduction (annual) |  | $ | Estimated from Day 1/2 findings
Build cost estimate (one-time) |  | $ | From Technical Architect estimate
Annual maintenance cost |  | $ | Typically 15-20% of build cost
Net Year 1 ROI |  | $ | #ERROR!
ROI Payback Period |  | months | #ERROR!
OPPORTUNITY 4 — ROI MODEL
Opportunity Name
AI Type
Brief Description
ROI Input | Value | Unit | Formula / Basis | Annual Value ($)
Hours saved per week (estimated) |  | hrs/wk | From Day 2 process scoring
Hourly cost used | 4 | $/hr | From assumptions above
Annual labour saving |  | $ | #ERROR!
Error / rework reduction (annual) |  | $ | Estimated from Day 1/2 findings
Build cost estimate (one-time) |  | $ | From Technical Architect estimate
Annual maintenance cost |  | $ | Typically 15-20% of build cost
Net Year 1 ROI |  | $ | #ERROR!
ROI Payback Period |  | months | #ERROR!
OPPORTUNITY 5 — ROI MODEL
Opportunity Name
AI Type
Brief Description
ROI Input | Value | Unit | Formula / Basis | Annual Value ($)
Hours saved per week (estimated) |  | hrs/wk | From Day 2 process scoring
Hourly cost used | 4 | $/hr | From assumptions above
Annual labour saving |  | $ | #ERROR!
Error / rework reduction (annual) |  | $ | Estimated from Day 1/2 findings
Build cost estimate (one-time) |  | $ | From Technical Architect estimate
Annual maintenance cost |  | $ | Typically 15-20% of build cost
Net Year 1 ROI |  | $ | #ERROR!
ROI Payback Period |  | months | #ERROR!

## Day 5 — Conversion
DAY 5 — ROADMAP PRESENTATION & CONVERSION
This is the ONLY session that matters for conversion — Invest extra preparation — Practice the delivery
PRE-DELIVERY CHECKLIST — Complete Before Day 5
Checklist Item | Owner | Done?
All 6 client deliverables completed and internally reviewed by second team member |  | ☐
ROI model uses client's actual data — NOT generic benchmarks |  | ☐
90-Day Roadmap timelines reviewed and approved by Technical Architect |  | ☐
Sprint Summary Presentation designed to Zylo brand standards (not a rough deck) |  | ☐
AI Readiness Score calculated and prominently displayed on slide 1 |  | ☐
Visual AI Opportunity Map (quadrant) included in presentation |  | ☐
Industry Benchmark section included in roadmap document |  | ☐
Proposal ready to send immediately if client says yes at end of Day 5 |  | ☐
Technical Architect on standby for technical Q&A during presentation |  | ☐
Loom debrief video recording plan confirmed (record same evening) |  | ☐
PRESENTATION STRUCTURE — 2.5 TO 3 HOURS
Time | Duration | Section | Facilitator Notes
0:00 | 5 min | Welcome & Sprint Recap | Thank everyone for the 5 days. Brief summary of what was covered.
0:05 | 10 min | AI Readiness Score | Present the score and tier. Explain what it means in context of their industry.
0:15 | 20 min | Full AI Opportunity Map | Walk through all 12 opportunities. Present the quadrant visual. Let client ask questions.
0:35 | 40 min | Top 5 Opportunities — Detail | For each: name, description, ROI estimate, build time, dependencies. Use plain language.
1:15 | 20 min | Industry Benchmark | Show where the client sits vs their peers. Make the urgency real.
1:35 | 30 min | 90-Day Roadmap | Phase 1 (0-30 days), Phase 2 (30-60 days), Phase 3 (60-90 days). Owners and outcomes.
2:05 | 15 min | Q&A | Open floor. Technical Architect available on standby for technical questions.
2:20 | 10 min | The Conversion Moment | Use the conversion script. Present the next step. Ask for the proposal request.
2:30 | 0 min | Close | Deliver all assets same day. Record Loom video same evening.
CONVERSION SCRIPT — USE THESE EXACT WORDS
"You now have a clear picture of the 3 AI systems that will have the highest impact on your business in the next 90 days. We've modelled the ROI — conservatively, you're looking at [X hours/month saved] and [$Y in annual savings] once Phase 1 is live. We can begin Phase 1 within [2 weeks]. The build will take [timeframe] and the total investment is in the range of [$X–$Y]. Would you like us to send a formal proposal so you can review the scope and sign off?"
OBJECTION HANDLING
Objection | Response
We need more time to think. | "Absolutely — I'll send everything over today so your team can review. Is there anything specific you'd like me to address in the proposal to make the decision easier?"
We don't have the budget right now. | "I understand. The ROI model shows Phase 1 pays for itself in [X months]. Would it help to structure the payment to start after the first milestone is live?"
Can we do this with our internal team? | "You could. The roadmap gives you everything you need to start. The question is timeline — our team can deliver Phase 1 in [X weeks]. How long would it take your internal team to get to the same place?"
We want to get other quotes. | "That makes sense. Just know that the roadmap you have is specific to your business — other vendors will be quoting based on a brief. We're quoting based on 5 days of understanding your operations."
Not the right time — maybe in 3 months. | "No problem at all. I'll check in then. Is it okay if I send a quick message in 8 weeks to see where things stand?"
DAY 5 OUTCOME LOG
Client Decision (Yes / Not Yet / No)
If Yes — Scope of Phase 1 requested
If Not Yet — Primary objection raised
Follow-up action scheduled
Follow-up date
Assigned rep for follow-up
Proposal sent date
Sprint conversion status (update in CRM)

## Sprint Retrospective
SPRINT RETROSPECTIVE — INTERNAL SESSION
Mandatory within 48 hours of Day 5 ¦ Attendees: Sprint Lead + BA + Technical Architect + Rep
SPRINT RECORD
Sprint Number
Client Company
Client Industry
AI Readiness Score Delivered
Tier Assigned (Starter/Builder/Scaler)
Day 5 Conversion Signal (Yes/Not Yet/No)
Sprint Lead
Date of Retrospective
RETROSPECTIVE QUESTIONS — 30-MINUTE AGENDA
1. What went well?
[Record 2-3 specific things that worked well in this sprint. Be specific about day, action, and outcome.]
2. What did NOT work?
[For each issue: On Day X, [what happened] — client reaction was [X] — we should have done [Y] instead]
3. What did we miss?
[What did the client reveal that we did not capture in the deliverables? Any signals we ignored?]
4. ONE change for the next sprint
[Agree on ONE specific, actionable change to make before the next sprint. Write it here.]
5. Quality assessment of deliverables
[Rate each deliverable: Business Profile / Process Inventory / Opportunity Map / ROI Model / Roadmap / Deck — Rate 1-5]
6. Client energy & engagement (Day 1–5)
[Describe the client's level of engagement across the sprint. What changed? Why?]
CUMULATIVE LEARNING LOG — Update after every sprint
Sprint # | Key Learning | Change Made to Framework | Impact Observed